## Roadmap
EHS Project Roadmap — Sumter, SC
Prepared by Charlie Ball for Kate Fowler · priorities 1-6 as assigned 31-Jul-2026 · targets run through Q2 2027
HOW TO USE: Column I is yours — add milestones, dates or comments there. Columns A-H are maintained by Charlie; Status (F) updates at each 1:1. Yellow = your input.
Dates are working targets, not committed dates. Anything already past its date shows Status = Overdue. D1 Ref is the task or knowledge ID in the EHS command centre.
Pri | Workstream | Milestone / Deliverable | Owner | Target Date | Status | D1 Ref | Dependency / Note | Kate — Milestone or Comment
1 | Respirators | Reschedule respirator inspection session | Charlie | 2026-08-14 | In progress | #737 |  | e.g. Gate review with Laura — 15-Sep
1 | Respirators | Semi-annual respirator inspection & cleaning | Charlie | 2026-09-30 | Not started | #470 | Benchmark compliance item
1 | Respirators | Respirator TPM / cleaning schedule confirmed in place | Charlie | 2026-09-30 | Not started | #626
1 | Respirators | NIOSH 25/26/27 forms organised into folders | Charlie | 2026-10-30 | Not started | #488
1 | Respirators | Respiratory protection program annual review documented | Charlie | 2026-11-30 | Not started | #523 | Rides the MESH element review
1 | Respirators | 2027 cycle scheduled + program closed out | Charlie | 2027-01-29 | Not started
2 | Scrap Bin Standardization | Walk scrap process with Kate, Jad, Ashwin | Charlie | 2026-08-21 | Not started | #525 | Prerequisite to back-plate design
2 | Scrap Bin Standardization | Scrap-bin back plate designed | Charlie / Ashwin | 2026-09-25 | Not started | #525 | Bins rotate off 2nd rotator; plate removes manual dumping
2 | Scrap Bin Standardization | Back plate fabricated + trialled | ATS / Ashwin | 2026-10-30 | Not started | #525
2 | Scrap Bin Standardization | Gray / blue cart standard defined (5S+ shed) | Charlie | 2026-10-30 | Not started
2 | Scrap Bin Standardization | Scrap-band standardization | Charlie | 2026-11-30 | Not started | #524 | One of the 5 roadmap risk-reduction projects
2 | Scrap Bin Standardization | Station cards issued for scrap handling | Charlie | 2027-02-26 | Not started | #524
2 | Scrap Bin Standardization | Standard rolled to all fab areas | Charlie | 2027-03-31 | Not started
3 | Lifting Devices | Vacuum lift solenoid project complete + GHG updated | Charlie | 2026-08-14 | Overdue | #691 | Benchmark #162, closure was 31-Jul-2026
3 | Lifting Devices | Crane inspections — Engineered Systems Inc | Kate | 2026-08-31 | In progress | #616 | Kate gathering cost for corporate across sites
3 | Lifting Devices | Q3 CapEx ~$250k received | Kate | 2026-08-31 | In progress | KN #467 | Budget gate for every purchase below
3 | Lifting Devices | Crane copper lifting devices — implementation plan | Charlie | 2026-08-28 | In progress | #696
3 | Lifting Devices | Replacements specified + quoted | Charlie / Kate | 2026-09-18 | Not started | KN #467 | Sheet lifter by paint line + 3 others + big-door lifter lasers to conveyors
3 | Lifting Devices | PO placed / 10% down | Kate | 2026-09-30 | Not started |  | 10% down locks the project permanently
3 | Lifting Devices | Crane inspection checklist verified for under-hook devices | Charlie | 2026-09-30 | Not started | #309 | Badger lesson learned — 27-stitch laceration
3 | Lifting Devices | Overhead crane PM ownership resolved | Charlie / Kate / Gireesh | 2026-10-30 | Not started | KN #442 | Disputed between supply chain and fab; no PM owner
3 | Lifting Devices | Setup-frame crane retired, A-frame replaced | Kate | 2026-11-27 | Not started | KN #407 | IES spare motor + parts; Hodges shipment held
3 | Lifting Devices | Yellow gym-hoist training documented in setup | Charlie / Marcus | 2026-11-27 | Not started | #618
3 | Lifting Devices | New lifting devices delivered + installed | Charlie | 2027-03-31 | Not started |  | Lead time dependent on Sep PO
3 | Lifting Devices | Post-install verification + WSRA updates | Charlie | 2027-04-30 | Not started
4 | Press Brakes | Press-brake safety alert (proper tool use) sent + confirmed | Charlie | 2026-08-07 | In progress | #687
4 | Press Brakes | Dept-wide comm: tools, or no hands on press brakes | Charlie | 2026-08-07 | Overdue | #561 / #653
4 | Press Brakes | Operator safety talk-down run | Charlie | 2026-08-14 | Overdue | #654
4 | Press Brakes | Formal near-miss record opened + Ashwin meeting | Charlie / Ashwin | 2026-08-14 | Not started | #623
4 | Press Brakes | Method sheet updated for changing dies | Charlie | 2026-08-21 | Overdue | #690
4 | Press Brakes | High-risk part population defined + safe routing method | Charlie / Ashwin | 2026-09-11 | Not started | #664 | Gates the routing milestone below
4 | Press Brakes | Press-brake training package built | Charlie | 2026-09-30 | Not started | #660 | Ron Brown / Marty Honey
4 | Press Brakes | AI camera / vision system specified + ordered | Charlie / Ashwin | 2026-10-30 | Not started | #521 | Needs Q3 CapEx confirmed
4 | Press Brakes | HRPs routed through the 4 safe press brakes + Amada | Charlie / Ashwin | 2026-11-30 | Not started | #521 | See Assumptions tab — definition of done
4 | Press Brakes | New-equipment safety standard written | Charlie | 2026-11-30 | Not started | #521 | Sumter leads this corporately
4 | Press Brakes | Weekly press-brake safety meeting | Charlie | 2026-12-31 | In progress | #658 | Recurring, runs through the project
4 | Press Brakes | AI camera system installed + validated | Charlie / Ashwin | 2027-03-31 | Not started | #521
5 | Laceration Risks | May lessons learned entered | Charlie | 2026-08-14 | Overdue | #545
5 | Laceration Risks | Finger-laceration reportable + corrective actions distributed | Kate | 2026-08-14 | Not started | #444
5 | Laceration Risks | Offal staging carts with protruding pieces eliminated | Charlie | 2026-09-25 | In progress | #515
5 | Laceration Risks | L-bracket / guard under conveyor machine return | Charlie | 2026-09-25 | Not started | #336 | Also addresses heat reflection
5 | Laceration Risks | Band-cutting standard work closed | Charlie | 2026-10-30 | Not started | #632 | Falling-channels near-miss
5 | Laceration Risks | Offal racks — ceiling, height control, accountability | Charlie | 2026-11-30 | Not started | #524 | One of the 5 roadmap risk-reduction projects
5 | Laceration Risks | Pallet-stacker procedural review + rack-lift procedure | Charlie / David | 2026-11-30 | Not started | #688 | Triggered on new stacker arrival
5 | Laceration Risks | Laceration risk register consolidated (bins, carts, conveyors, pallets) | Charlie | 2026-12-18 | Not started |  | Covers 4 prior recordables
5 | Laceration Risks | 2027 verification pass + WSRA integration | Charlie | 2027-03-31 | Not started
6 | Laser Loading | Trumpf contacted re OEM loading method | Charlie | 2026-08-14 | In progress | #554 | Roller balls up or down; is the clamshell the right device
6 | Laser Loading | Ashwin reviews Laser 1 loading mod for replication | Ashwin | 2026-08-28 | Not started | #554
6 | Laser Loading | Scope confirmed against 2027 laser divestiture | Charlie / Kate | 2026-09-30 | Not started | KN #416 | See Assumptions tab — two suppliers buying the lasers
6 | Laser Loading | Laser 3 near-miss corrective actions closed | Charlie | 2026-09-25 | Not started | KN #441 | Sheet slid, creased 480V control-panel line
6 | Laser Loading | Laser 2 & 3 loading mods implemented | Ashwin / ATS | 2026-11-30 | Not started | #554 | Conditional on divestiture scope above
6 | Laser Loading | Overhead crane maintenance / PM restored | Kate / Gireesh | 2026-12-18 | Not started | KN #442 | ~10 yrs unmaintained; single point of failure for laser loading

## Summary
Roadmap Summary
All figures calculated from the Roadmap tab — they update as Status changes.
Pri | Workstream | Milestones | Complete | In progress | Overdue | Not started | % Complete | Last target date
1 | Respirators | 6
2 | Scrap Bin Standardization | 7
3 | Lifting Devices | 12
4 | Press Brakes | 12
5 | Laceration Risks | 9
6 | Laser Loading | 6
TOTAL
Counts read Status on the Roadmap tab; % Complete = Complete / Milestones. Update Status there and these refresh.

## Assumptions & Open Items
Assumptions and Open Items
These drive the dates on the Roadmap tab. If an assumption is wrong the dates move — flag it and I will reissue.
# | Item | Assumption made | What I need from you
1 | Press brakes — definition of done | I have taken 'done' to mean all three: high-risk parts identified and routed through the 4 safe press brakes and the Amada, the AI camera system installed and validated, and the new-equipment standard written. Routing and the standard land in 2026; camera install runs into Q1 2027 on lead time. | Confirm this is the finish line you have in mind, or tell me which of the three you are dating.
2 | Laser loading vs 2027 divestiture | Two suppliers are buying the lasers, punches and spot welders as Sumter moves to switchboard-only in 2027 (KN #416). I have scoped Laser 2 and 3 loading mods as conditional and put a scope-confirmation gate in September before any spend. | Whether we invest in loading mods for assets that leave in 2027, or hold at controls and training only.
3 | Q3 CapEx gate | Lifting device purchases and the AI camera order both assume the ~$250k Q3 CapEx lands in August as planned. PO placed September with 10% down to lock it. | Confirm the August timing and whether the AI camera comes out of this pot or a separate one.
4 | Respirators scope | Treated as a compliance-maintenance workstream, not a build — inspection cadence, TPM schedule, forms and the annual program review. No new respirator selection or fit-test program assumed. | Confirm nothing larger is intended here.
5 | Owner assignments | Where a task had no owner in the system I have put myself. Ashwin carries the engineering reviews, ATS the fabrication and install. | Correct anything I have assigned to the wrong person.
6 | Overdue items | Five items were already past their date at issue and are dated forward into August: vacuum lift solenoid (Benchmark #162), the two press-brake communications, the operator talk-down and the die-change method sheet. | No action needed — flagging so the red on the sheet is not a surprise.
7 | Dates are targets | Working targets for sequencing and 1:1 review, not committed dates to corporate. Nothing here has been shared outside the two of us. | Tell me which of these you want turned into committed dates.